## 18-Day Task Plan
MHS — Diabetes Reversal Webinar Funnel + Sales CRM
18-Day Work Plan — Daily Task Breakdown & Status
Project |  | MHS Diabetes Reversal Webinar Funnel (Meta + YouTube) and Sales CRM
Reporting Period |  | 22 Apr 2026 – 21 May 2026
Total Working Days |  | 18 (3 – 4 tasks per day)
Total Tasks |  | 72
Tech Stack |  | Vite/React SPAs · Node.js/Express · PostgreSQL · Tata Smartflo telephony
Overall Status |  | 71 of 72 tasks Completed · 1 In Progress
Day | Date | Work Phase | Task # | Task Description | Status
Day 1 | 22 Apr 2026 | Project Setup & Funnel Foundation | 1.1 | Initialised the MHS Diabetes Reversal webinar funnel project (Vite/React) | Completed
|  |  | 1.2 | Built the initial multi-step registration funnel screens | Completed
|  |  | 1.3 | Configured Vercel deployment for the frontend apps | Completed
|  |  | 1.4 | Configured Render backend deployment and fixed API rewrite paths | Completed
Day 2 | 24 Apr 2026 | Funnel UI Redesign | 2.1 | Redesigned all funnel screens and shared components | Completed
|  |  | 2.2 | Reworked the Disqualified page and WhatsApp bottom-sheet UI | Completed
|  |  | 2.3 | Added the language-selection popup as a second step in Screen1A | Completed
|  |  | 2.4 | Fixed the popup step transition to a swipe-up animation | Completed
Day 3 | 25 Apr 2026 | UI Overhaul & State Persistence | 3.1 | Merged funnel cards and removed the redundant Screen3 | Completed
|  |  | 3.2 | Redesigned Screen4 and the WhatsApp sheet layout | Completed
|  |  | 3.3 | Added localStorage persistence so funnel progress survives reloads | Completed
|  |  | 3.4 | Merged the UI-overhaul branch into master | Completed
Day 4 | 26 Apr 2026 | Performance & Theme Pass | 4.1 | GPU-accelerated animations across all funnel screens | Completed
|  |  | 4.2 | Disabled the heavy gear background on mobile devices | Completed
|  |  | 4.3 | Applied the light-lavender theme with liquid-glass cards | Completed
|  |  | 4.4 | Replaced slide page transitions with fast opacity/fade | Completed
Day 5 | 27 Apr 2026 | Architecture: 3-App Split & Postgres | 5.1 | Reorganised the repo into frontend / backend / database folders | Completed
|  |  | 5.2 | Migrated the database from Supabase to PostgreSQL | Completed
|  |  | 5.3 | Built the standalone /whatsapp redirect page with day-based link | Completed
|  |  | 5.4 | Split into 3 independent apps and integrated Meta Pixel tracking | Completed
Day 6 | 28 Apr 2026 | Real-time Config & SSE | 6.1 | Added real-time webinar config updates via Server-Sent Events | Completed
|  |  | 6.2 | Built the scheduled WhatsApp link auto-swap feature | Completed
|  |  | 6.3 | Performance pass — async fonts, build chunking, image compression | Completed
|  |  | 6.4 | Added the first automated test suite and fixed blank-page bugs | Completed
Day 7 | 29 Apr 2026 | WhatsApp Editor, Sheets Sync & QA | 7.1 | Improved the WhatsApp link editor — 12h picker and second schedule slot | Completed
|  |  | 7.2 | Added Google Sheets daily leads sync | Completed
|  |  | 7.3 | Built the 'Not Tamil products' page for Tamil-unknown users | Completed
|  |  | 7.4 | Delivered a 37-test QA suite and cleaned up the admin UI | Completed
Day 8 | 30 Apr – 02 May 2026 | Leads Management & Home Dashboard | 8.1 | Added bulk-delete for the leads table | Completed
|  |  | 8.2 | Built the Home Dashboard with click analytics for all 10 funnel buttons | Completed
|  |  | 8.3 | Added drop-off summary boxes and an Ad Source column | Completed
|  |  | 8.4 | Added leads-table pagination (10 per page) | Completed
Day 9 | 05 – 06 May 2026 | Tracking & Automation Hardening | 9.1 | Added a duplicate-leads filter and fixed bulk delete for large selections | Completed
|  |  | 9.2 | Added page-visit tracking with current/next webinar fields | Completed
|  |  | 9.3 | Built automated webinar management with WhatsApp link rotation | Completed
|  |  | 9.4 | Made the entire admin dashboard mobile-responsive | Completed
Day 10 | 09 May 2026 | CRM App & Tata Smartflo Integration | 10.1 | Built the new CRM application | Completed
|  |  | 10.2 | Integrated Tata Smartflo cloud telephony | Completed
|  |  | 10.3 | Added caller workload tools | Completed
|  |  | 10.4 | Fixed webinar batch numbering and added call-form fields | Completed
Day 11 | 10 May 2026 | Auto-Call Workflow & YouTube Pipeline | 11.1 | Added the YouTube lead pipeline alongside the Meta funnel | Completed
|  |  | 11.2 | Rewrote the auto-call workflow | Completed
|  |  | 11.3 | Automated call-end detection and dropped the manual End Call button | Completed
|  |  | 11.4 | Fixed false call-retry when both legs had answered | Completed
Day 12 | 10 May 2026 | Call Pipeline Stabilisation | 12.1 | Fixed Tata call-leg fragmentation in the polling logic | Completed
|  |  | 12.2 | Aggregated call signals across DB fragments for the same lead | Completed
|  |  | 12.3 | Fixed 9 call-flow modal and webhook bugs | Completed
|  |  | 12.4 | Restored the SmartFlow extension-check overlay on Start Auto-Call | Completed
Day 13 | 11 May 2026 | Missed Calls & Leads Alerts | 13.1 | Built the Missed Calls page for inbound customer calls | Completed
|  |  | 13.2 | Auto-synced inbound missed calls from the Tata CDR API | Completed
|  |  | 13.3 | Built the leads alert system with source-aware link rotation | Completed
|  |  | 13.4 | Surfaced all 14 call-form fields in the completed-lead card | Completed
Day 14 | 12 May 2026 | Sales Analytics & Meta Ads | 14.1 | Built the Sales Performance dashboard | Completed
|  |  | 14.2 | Integrated Meta Ads with verified-Meta tracking | Completed
|  |  | 14.3 | Fixed marketing-analytics bugs | Completed
|  |  | 14.4 | Reworked the CTA pulse animation to pure CSS keyframes | Completed
Day 15 | 13 May 2026 | Visitor Tracking & Caller Controls | 15.1 | Added unique-visitor tracking (UUID + IP/UA fallback + phone merge) | Completed
|  |  | 15.2 | Built the DNP button with a two-press confirmation banner | Completed
|  |  | 15.3 | Added the caller break flow (Tea / Lunch / Other reason picker) | Completed
|  |  | 15.4 | Added the queue-end refill modal | Completed
Day 16 | 14 May 2026 | Production Hardening | 16.1 | Bullet-proofed the call + form pipeline for multi-caller production | Completed
|  |  | 16.2 | Gated the Recall button to the active form window only | Completed
|  |  | 16.3 | Hardened the 5-second post-call timers and fixed banner bugs | Completed
|  |  | 16.4 | Built the Next Batch page and polished Sales Performance | Completed
Day 17 | 16 – 18 May 2026 | Multi-Service Split & Dev Environment | 17.1 | Added a SmartFlow concurrency cap of 15 with auto-pause and refill modal | Completed
|  |  | 17.2 | Added DISABLE_SCHEDULERS / DISABLE_LEAD_LISTENER env toggles | Completed
|  |  | 17.3 | Split the backend into 3 separate service folders | Completed
|  |  | 17.4 | Integrated the single-page Meta funnel and polished the CRM dashboard | Completed
Day 18 | 19 – 21 May 2026 | CRM Activity Log & YT Conversions | 18.1 | Round-robin skip of duplicate WhatsApp numbers within the same webinar | Completed
|  |  | 18.2 | Built the CRM single-tag activity log, source badges and notifications view | Completed
|  |  | 18.3 | Added the YouTube funnel Google Ads ATC conversion firing | Completed
|  |  | 18.4 | Caller robot voice nudges — caller modules and audio assets still in progress | In Progress
TOTAL — 18 working days · 72 tasks · 71 Completed, 1 In Progress |  |  |  |  | 98.6%